SECTION 013300 - SUBMITTAL PROCEDURES

Revise this Section by deleting and inserting text to meet Project-specific requirements.

GENERAL

SUMMARY

Section includes requirements for the submittal schedule and administrative and procedural requirements for submitting Shop Drawings, Product Data, Samples, and other submittals.

Related Requirements:

Retain subparagraphs below to cross-reference requirements Contractor might expect to find in this Section but are specified in other Sections.

Section 013200 "Construction Progress Documentation" for submitting schedules and reports, including Contractor's construction schedule.

Section 017823 "Operation and Maintenance Data" for submitting operation and maintenance manuals.

Section 017839 "Project Record Documents" for submitting record Drawings, record Specifications, and record Product Data.

Section 017900 "Demonstration and Training" for submitting video recordings of demonstration of equipment and training of Owner's personnel.

DEFINITIONS

Retain terms that remain after this Section has been edited for a project.

Action Submittals:  Written and graphic information and physical samples that require Architect's responsive action.

Informational Submittals:  Written and graphic information and physical samples that do not require Architect's responsive action.  Submittals may be rejected for not complying with requirements.

ACTION SUBMITTALS

Revise "Submittal Schedule" Paragraph below to suit Project.  If there is an office submittal review sequence policy, insert specific requirements.  See Evaluations for discussion on submittal review sequence policies.

Submittal Schedule:  Submit a schedule of submittals, arranged in chronological order by dates required by construction schedule.  Include time required for review, ordering, manufacturing, fabrication, and delivery when establishing dates.  Include additional time required for making corrections or revisions to submittals noted by Architect and additional time for handling and reviewing submittals required by those corrections.

SUBMITTAL ADMINISTRATIVE REQUIREMENTS

See Evaluations for cautions on use of Architect's digital data files, in "Architect's Digital Data Files" Paragraph below, for submittals.

Architect's Digital Data Files:  Electronic copies of digital data files of the Contract Drawings will[ not] be provided by Architect for Contractor's use in preparing submittals.

Retain subparagraph below if Architect's digital data files will be made available to Contractor.  Examples of additional project-specific limitations and restrictions that specifier may wish to add below include limitation to files that already exist, limitations on incorporating revisions, limitations on availability of Architect's consultant files, limitation of digital drawing system formats, limitation on digital drawing entity attributes and layering, restrictions on Contractor's use, cost of providing files, mode of transmittal, and delivery time.

Architect will furnish Contractor one set of digital data drawing files of the Contract Drawings for use in preparing Shop Drawings[ and Project record drawings].

Architect makes no representations as to the accuracy or completeness of digital data drawing files as they relate to the Contract Drawings.

Contractor shall execute a data licensing agreement in the form of [AIA Document C106, Digital Data Licensing Agreement] [Agreement included in Project Manual] [Agreement form acceptable to Owner and Architect].

<Insert conditions on which digital data drawing files will made available>.

Coordination:  Coordinate preparation and processing of submittals with performance of construction activities.

Coordinate each submittal with fabrication, purchasing, testing, delivery, other submittals, and related activities that require sequential activity.

Retain subparagraph below if one submittal has an impact on another submittal.  Submittals that require concurrent review should be so indicated in those Sections.

Coordinate transmittal of different types of submittals for related parts of the Work so processing will not be delayed because of need to review submittals concurrently for coordination.

Architect reserves the right to withhold action on a submittal requiring coordination with other submittals until related submittals are received.

Processing Time:  Allow time for submittal review, including time for resubmittals, as follows.  Time for review shall commence on Architect's receipt of submittal.  No extension of the Contract Time will be authorized because of failure to transmit submittals enough in advance of the Work to permit processing, including resubmittals.

Initial Review:  Allow 15 days for initial review of each submittal.  Allow additional time if coordination with subsequent submittals is required.  Architect will advise Contractor when a submittal being processed must be delayed for coordination.

Intermediate Review:  If intermediate submittal is necessary, process it in same manner as initial submittal.

Resubmittal Review:  Allow 15 days for review of each resubmittal.

Retain "Paper Submittals" Paragraph below if requiring paper copies of submittals instead of electronic submittals.

Paper Submittals:  Place a permanent label or title block on each submittal item for identification.

Indicate name of firm or entity that prepared each submittal on label or title block.

Provide a space approximately [6 by 8 inches (150 by 200 mm)] <Insert dimensions> on label or beside title block to record Contractor's review and approval markings and action taken by Architect.

Include the following information for processing and recording action taken:

Project name.

Date.

Name of Architect.

Name of Construction Manager.

Name of Contractor.

Name of subcontractor.

Name of supplier.

Name of manufacturer.

Revise first subparagraph below to suit Project and office practice.

Submittal number or other unique identifier, including revision identifier.

Submittal number shall use Specification Section number followed by a decimal point and then a sequential number (e.g., 061000.01).  Resubmittals shall include an alphabetic suffix after another decimal point (e.g., 061000.01.A).

Number and title of appropriate Specification Section.

Drawing number and detail references, as appropriate.

Location(s) where product is to be installed, as appropriate.

Other necessary identification.

Revise "Additional Paper Copies" Subparagraph below to suit Project and office policy.  Marking numerous copies of submittals can be time consuming.

Additional Paper Copies:  Unless additional copies are required for final submittal, and unless Architect observes noncompliance with provisions in the Contract Documents, initial submittal may serve as final submittal.

Submit one copy of submittal to concurrent reviewer in addition to specified number of copies to Architect.

Transmittal for Paper Submittals:  Assemble each submittal individually and appropriately for transmittal and handling.  Transmit each submittal using a transmittal form.  Architect will return without review submittals received from sources other than Contractor.

Retain one of two "Transmittal Form for Paper Submittals" subparagraphs below.  Typically retain first subparagraph unless transmittal forms commonly used by contractors, in second subparagraph, are acceptable.  If retaining last option in first subparagraph, insert a sample of the form in Project Manual.

Transmittal Form for Paper Submittals:  Use [AIA Document G810] [CSI Form 12.1A].

Transmittal Form for Paper Submittals:  Provide locations on form for the following information:

Project name.

BJC Ppoject number

Date.

Destination (To:).

Source (From:).

Name and address of Architect.

Name of Construction Manager.

Name of Contractor.

Name of firm or entity that prepared submittal.

Names of subcontractor, manufacturer, and supplier.

Category and type of submittal.

Submittal purpose and description.

Specification Section number and title.

Specification paragraph number or drawing designation and generic name for each of multiple items.

Drawing number and detail references, as appropriate.

Indication of full or partial submittal.

Transmittal number, numbered consecutively.

Submittal and transmittal distribution record.

Remarks.

Signature of transmitter.

Retain "Electronic Submittals" Paragraph below if requiring electronic submittals instead of paper submittals.

Electronic Submittals:  Identify and incorporate information in each electronic submittal file as follows:

Requirement in first subparagraph below can be performed automatically using PDF publishing software.

Assemble complete submittal package into a single indexed file incorporating submittal requirements of a single Specification Section and transmittal form with links enabling navigation to each item.

Name file with submittal number or other unique identifier, including revision identifier.

Revise first subparagraph below to suit Project and office practice.

File name shall use project identifier and Specification Section number followed by a decimal point and then a sequential number (e.g., LNHS-061000.01).  Resubmittals shall include an alphabetic suffix after another decimal point (e.g., LNHS-061000.01.A).

Requirement in first subparagraph below can be performed using PDF publishing software.

Provide means for insertion to permanently record Contractor's review and approval markings and action taken by Architect.

Transmittal Form for Electronic Submittals:  Use electronic form acceptable to Owner, containing the following information:

Project name.

BJC project number

Date.

Name and address of Architect.

Name of Construction Manager.

Name of Contractor.

Name of firm or entity that prepared submittal.

Names of subcontractor, manufacturer, and supplier.

Category and type of submittal.

Submittal purpose and description.

Specification Section number and title.

Specification paragraph number or drawing designation and generic name for each of multiple items.

Drawing number and detail references, as appropriate.

Location(s) where product is to be installed, as appropriate.

Related physical samples submitted directly.

Indication of full or partial submittal.

Transmittal number[, numbered consecutively].

Submittal and transmittal distribution record.

Other necessary identification.

Remarks.

Metadata:  Include the following information as keywords in the electronic submittal file metadata:

Project name.

Number and title of appropriate Specification Section.

Manufacturer name.

Product name.

Options:  Identify options requiring selection by Architect.

Deviations:  Identify deviations from the Contract Documents on submittals.

Resubmittals:  Make resubmittals in same form and number of copies as initial submittal.

Note date and content of previous submittal.

Note date and content of revision in label or title block and clearly indicate extent of revision.

Resubmit submittals until they are marked with approval notation from Architect's action stamp.

Distribution:  Furnish copies of final submittals to manufacturers, subcontractors, suppliers, fabricators, installers, authorities having jurisdiction, and others as necessary for performance of construction activities.  Show distribution on transmittal forms.

Use for Construction:  Retain complete copies of submittals on Project site.  Use only final action submittals that are marked with approval notation from Architect's action stamp.

PRODUCTS

SUBMITTAL PROCEDURES

General Submittal Procedure Requirements:

Retain one of first two subparagraphs below if required.

Post electronic submittals as PDF electronic files directly to [Project Web site] [Architect's FTP site] specifically established for Project.

Architect will return annotated file.  Annotate and retain one copy of file as an electronic Project record document file.

Submit electronic submittals via email as PDF electronic files.

Architect will return annotated file.  Annotate and retain one copy of file as an electronic Project record document file.

Retain "Action Submittals" and "Informational Submittals" subparagraphs below as default requirements for paper copies of submittals; other quantity requirements may be included with individual submittal requirements elsewhere in this article.  Additional copies may be required for projects with a construction manager or a commissioning authority.

Action Submittals:  Submit [three] <Insert number> paper copies of each submittal unless otherwise indicated.  Architect will return [two] <Insert number> copies.

Informational Submittals:  Submit [two] <Insert number> paper copies of each submittal unless otherwise indicated.  Architect will not return copies.

Certificates and Certifications Submittals:  Provide a statement that includes signature of entity responsible for preparing certification.  Certificates and certifications shall be signed by an officer or other individual authorized to sign documents on behalf of that entity.

Retain first subparagraph below if requiring digitally signed electronic submittals.  Coordinate requirements in individual Specification Sections.  PDF publishing software such as Adobe Acrobat allows the publisher of a document to apply a certified signature to a completed document verifying the authenticity of the document and the signer.

Provide a digital signature with digital certificate on electronically-submitted certificates and certifications where indicated.

Retain first subparagraph below when one or more individual Specification Sections includes requirements for notarized signature on certificates and certifications.

Provide a notarized statement on original paper copy certificates and certifications where indicated.

Additional copies may be required for each type of submittal in remaining paragraphs below for projects with a construction manager or a commissioning authority.

Product Data:  Collect information into a single submittal for each element of construction and type of product or equipment.

If information must be specially prepared for submittal because standard published data are not suitable for use, submit as Shop Drawings, not as Product Data.

Mark each copy of each submittal to show which products and options are applicable.

Include the following information, as applicable:

Manufacturer's catalog cuts.

Manufacturer's product specifications.

Standard color charts.

Statement of compliance with specified referenced standards.

Testing by recognized testing agency.

Application of testing agency labels and seals.

Notation of coordination requirements.

Availability and delivery time information.

For equipment, include the following in addition to the above, as applicable:

Wiring diagrams showing factory-installed wiring.

Printed performance curves.

Operational range diagrams.

Clearances required to other construction, if not indicated on accompanying Shop Drawings.

Submit Product Data before or concurrent with Samples.

Retain subparagraph below unless default submittal format specified elsewhere in this article applies.

Submit Product Data in the following format:

Retain one of two subparagraphs below unless default submittal format specified elsewhere in this article applies.

PDF electronic file.

[Three] <Insert number> paper copies of Product Data unless otherwise indicated.  Architect[, through Construction Manager,] will return [two] <Insert number> copies.

Shop Drawings:  Prepare Project-specific information, drawn accurately to scale.  Do not base Shop Drawings on reproductions of the Contract Documents or standard printed data[, unless submittal based on Architect's digital data drawing files is otherwise permitted].

Preparation:  Fully illustrate requirements in the Contract Documents.  Include the following information, as applicable:

Comply with Owner's requirements and office policy.

Identification of products.

Schedules.

Compliance with specified standards.

Notation of coordination requirements.

Notation of dimensions established by field measurement.

Relationship and attachment to adjoining construction clearly indicated.

Seal and signature of professional engineer if specified.

Revise "Sheet Size" Subparagraph below to establish a standard sheet size and format.

Sheet Size:  Except for templates, patterns, and similar full-size drawings, submit Shop Drawings on sheets at least [8-1/2 by 11 inches (215 by 280 mm), but no larger than 30 by 42 inches (750 by 1067 mm)] <Insert dimensions>.

Retain subparagraph below unless default submittal format specified elsewhere in this article applies.

Submit Shop Drawings in the following format:

Retain one of three subparagraphs below unless default submittal format specified elsewhere in this article applies.

PDF electronic file.

Retain one of two subparagraphs below if requiring paper copy submittal.  First subparagraph assumes Architect and Contractor will make copies from opaque print.

[Two] opaque (bond) copies of each submittal.  Architect[, through Construction Manager,] will return [one] <Insert number> copy(ies).

[Three] <Insert number> opaque copies of each submittal.  Architect[ and Construction Manager] will retain [two] <Insert number> copies; remainder will be returned.

Samples:  Submit Samples for review of kind, color, pattern, and texture for a check of these characteristics with other elements and for a comparison of these characteristics between submittal and actual component as delivered and installed.

Transmit Samples that contain multiple, related components such as accessories together in one submittal package.

Identification:  Attach label on unexposed side of Samples that includes the following:

Generic description of Sample.

Product name and name of manufacturer.

Sample source.

Number and title of applicable Specification Section.

Retain paragraph below for projects utilizing electronic submittals to provide complete electronic submittal record of Sample items.

For projects where electronic submittals are required, provide corresponding electronic submittal of Sample transmittal, digital image file illustrating Sample characteristics, and identification information for record.

Disposition:  Maintain sets of approved Samples at Project site, available for quality-control comparisons throughout the course of construction activity.  Sample sets may be used to determine final acceptance of construction associated with each set.

Retain first subparagraph below if required.

Samples that may be incorporated into the Work are indicated in individual Specification Sections.  Such Samples must be in an undamaged condition at time of use.

Samples not incorporated into the Work, or otherwise designated as Owner's property, are the property of Contractor.

Revise "Samples for Initial Selection" Subparagraph below if Project requires a different procedure.  Consider indicating Samples for initial selection as a separate item in the submittal schedule.  Delete subparagraph if colors and other characteristics are preselected and specified or scheduled.

Samples for Initial Selection:  Submit manufacturer's color charts consisting of units or sections of units showing the full range of colors, textures, and patterns available.

Number of Samples:  Submit [one] <Insert number> full set(s) of available choices where color, pattern, texture, or similar characteristics are required to be selected from manufacturer's product line.  Architect  will return submittal with options selected.

"Samples for Verification" Subparagraph below can be used with or without Samples for initial selection.  Revise to suit Project.

Samples for Verification:  Submit full-size units or Samples of size indicated, prepared from same material to be used for the Work, cured and finished in manner specified, and physically identical with material or product proposed for use, and that show full range of color and texture variations expected.  Samples include, but are not limited to, the following:  partial sections of manufactured or fabricated components; small cuts or containers of materials; complete units of repetitively used materials; swatches showing color, texture, and pattern; color range sets; and components used for independent testing and inspection.

Number of Samples:  Submit [four] <Insert number> sets of Samples.  Architect will retain [two] <Insert number> Owner will receive [one] <insert number> Sample sets; remainder will be returned.[  Mark up and retain one returned Sample set as a project record sample.]

If variation in color, pattern, texture, or other characteristic is inherent in material or product represented by a Sample, submit at least [three] <Insert number> sets of paired units that show approximate limits of variations.

"Product Schedule" Paragraph below describes Contractor's submittal in tabular form detailing product and installation requirements for an individual Section.

Product Schedule:  As required in individual Specification Sections, prepare a written summary indicating types of products required for the Work and their intended location.  Include the following information in tabular form:

Retain subparagraph below unless default submittal format specified elsewhere in this article applies.

Submit product schedule in the following format:

Retain one of two subparagraphs below unless default submittal format specified elsewhere in this article applies.

PDF electronic file.

[Three] <Insert number> paper copies of product schedule or list unless otherwise indicated.  Architect[, through Construction Manager,] will return [two] <Insert number> copies.

Coordination Drawings Submittals:  Comply with requirements specified in Section 013100 "Project Management and Coordination."

Contractor's Construction Schedule:  Comply with requirements specified in Section 013200 "Construction Progress Documentation."

Application for Payment and Schedule of Values:  Comply with requirements specified in Section 012900 "Payment Procedures.

Test and Inspection Reports and Schedule of Tests and Inspections Submittals:  Comply with requirements specified in Section 014000 "Quality Requirements."

Closeout Submittals and Maintenance Material Submittals:  Comply with requirements specified in Section 017700 "Closeout Procedures."

Maintenance Data:  Comply with requirements specified in Section 017823 "Operation and Maintenance Data."

Retain "LEED Submittals" Paragraph below to ensure that requirements for LEED documentation are coordinated with requirements for other submittals.

Qualification Data:  Prepare written information that demonstrates capabilities and experience of firm or person.  Include lists of completed projects with project names and addresses, contact information of architects and owners, and other information specified.

Welding Certificates:  Prepare written certification that welding procedures and personnel comply with requirements in the Contract Documents.  Submit record of Welding Procedure Specification and Procedure Qualification Record on AWS forms.  Include names of firms and personnel certified.

Insert definition of Contractor certificates here if required by individual Specification Sections.  See Evaluations.

Installer Certificates:  Submit written statements on manufacturer's letterhead certifying that Installer complies with requirements in the Contract Documents and, where required, is authorized by manufacturer for this specific Project.

Manufacturer Certificates:  Submit written statements on manufacturer's letterhead certifying that manufacturer complies with requirements in the Contract Documents.  Include evidence of manufacturing experience where required.

Product Certificates:  Submit written statements on manufacturer's letterhead certifying that product complies with requirements in the Contract Documents.

Material Certificates:  Submit written statements on manufacturer's letterhead certifying that material complies with requirements in the Contract Documents.

Material Test Reports:  Submit reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting test results of material for compliance with requirements in the Contract Documents.

Product Test Reports:  Submit written reports indicating that current product produced by manufacturer complies with requirements in the Contract Documents.  Base reports on evaluation of tests performed by manufacturer and witnessed by a qualified testing agency, or on comprehensive tests performed by a qualified testing agency.

Research Reports:  Submit written evidence, from a model code organization acceptable to authorities having jurisdiction, that product complies with building code in effect for Project.

Schedule of Tests and Inspections:  Comply with requirements specified in Section 014000 "Quality Requirements."

Preconstruction Test Reports:  Submit reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting results of tests performed before installation of product, for compliance with performance requirements in the Contract Documents.

Compatibility Test Reports:  Submit reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting results of compatibility tests performed before installation of product.  Include written recommendations for primers and substrate preparation needed for adhesion.

Field Test Reports:  Submit written reports indicating and interpreting results of field tests performed either during installation of product or after product is installed in its final location, for compliance with requirements in the Contract Documents.

Usually retain "Design Data" Paragraph below for products, systems, and assemblies whose requirements are fully developed in the Contract Documents.  See "Delegated-Design Services" Article for submittal requirements where delegated-design services are required.

Design Data:  Prepare and submit written and graphic information, including, but not limited to, performance and design criteria, list of applicable codes and regulations, and calculations.  Include list of assumptions and other performance and design criteria and a summary of loads.  Include load diagrams if applicable.  Provide name and version of software, if any, used for calculations.  Include page numbers.

DELEGATED-DESIGN SERVICES

Performance and Design Criteria:  Where professional design services or certifications by a design professional are specifically required of Contractor by the Contract Documents, provide products and systems complying with specific performance and design criteria indicated.

If criteria indicated are not sufficient to perform services or certification required, submit a written request for additional information to Architect.

Delegated-Design Services Certification:  In addition to Shop Drawings, Product Data, and other required submittals, submit [digitally signed PDF electronic file] [and] [three] <Insert number> paper copies of certificate, signed and sealed by the responsible design professional, for each product and system specifically assigned to Contractor to be designed or certified by a design professional.

Indicate that products and systems comply with performance and design criteria in the Contract Documents.  Include list of codes, loads, and other factors used in performing these services.

EXECUTION

CONTRACTOR'S REVIEW

Action and Informational Submittals:  Review each submittal and check for coordination with other Work of the Contract and for compliance with the Contract Documents.  Note corrections and field dimensions.  Mark with approval stamp before submitting to Architect.

Project Closeout and Maintenance Material Submittals:  See requirements in Section 017700 "Closeout Procedures."

Approval Stamp:  Stamp each submittal with a uniform, approval stamp.  Include Project name and location, submittal number, Specification Section title and number, name of reviewer, date of Contractor's approval, and statement certifying that submittal has been reviewed, checked, and approved for compliance with the Contract Documents.

ARCHITECT'S[ AND CONSTRUCTION MANAGER'S] ACTION

General:  Architect will not review submittals that do not bear Contractor's approval stamp and will return them without action.

Most architects (and construction managers) use a stamp to indicate action taken on submittals.  Retain "Action Submittals" Paragraph below if using such a stamp, or substitute another system to comply with office policy or Owner's requirements.  AIA Document A201 states that "the Architect will review and approve or take other appropriate action upon the Contractor's submittals." AIA Document A201/CMa states that Construction Manager will review and approve submittals before transmitting those recommended for approval to Architect.

Action Submittals:  Architect will review each submittal, make marks to indicate corrections or revisions required, and return it.  Architect will stamp each submittal with an action stamp and will mark stamp appropriately to indicate [action.] [action, as follows:]

On advice of counsel, retain appropriate terms for action stamp and insert term and explanation of each action taken in subparagraph below.

<Insert description of each action indicated on Architect's (and Construction Manager's) stamp>.

Informational Submittals:  Architect will review each submittal and will not return it, or will return it if it does not comply with requirements.  Architect will forward each submittal to appropriate party.

Incomplete submittals are unacceptable, will be considered nonresponsive, and will be returned for resubmittal without review.

Submittals not required by the Contract Documents may not be reviewed and may be discarded.

END OF SECTION 01 33 00